## Sheet1
Items to be improved | Description | Improvement direction | Person responsible | Expected start date | Actual start date | Expected completion date | Actual completion date | duration | Improve immediately | Confirmation | appendix
The saturation of the lower glass point Xiaoli Pill is 65% |  | The improvement direction for 'The saturation of the lower glass point Xiaoli Pill is 65%' is: 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3. Automated level inspection: simple and automated import 4. Merge and rearrange new job elements. | LiXX | 10/8/24 | 10/8/24 | 10/15/24 | 10/15/24 | 7 | yes | LiXX
Bottom glass electrophoresis tank+UVFixed baking operation saturation79.2% |  | The 'Improvement direction' for 'Bottom glass electrophoresis tank+UVFixed baking operation saturation79.2%' is as follows: 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3. Automated level inspection: simple and automated import 4. Merge and rearrange new job elements. | LiXX | 10/8/24 | 10/8/24 | 10/15/24 | 10/15/24 | 7 | yes | LiXX | LiXX
Xiaoliwan wax+Paste conductive foam+Lower glass glue frame dispensing operation saturation75% |  | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3. Automated level inspection: simple and automated import 4. Merge and rearrange new job elements | LiXX | 10/8/24 | 10/8/24 | 10/15/24 | 10/15/24 | 7 | yes | LiXX | LiXX
The upper and lower glass bonding saturation is 67.5% |  | The improvement direction for 'The upper and lower glass bonding saturation is 67.5%' is as follows: 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3. Automated level inspection: simple and automated import 4. Merge and rearrange new job elements. | LiXX | 10/8/24 | 10/8/24 | 10/15/24 | 10/15/24 | 7 | yes | LiXX
Five-in-one front&back saturation53.2% |  | The 'Improvement direction' for 'Five-in-one front&back saturation53.2%' is to reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards. | LiXX | 10/8/24 | 10/8/24 | 10/15/24 | 10/15/24 | 7 |  | LiXX