## Standard work accumulation tab
Standard work accumulation table improvement project table
Project name |  | Disc X4 version PSS assembly process standard operation |  | admit | plumXX |  |  | tabulation | XuXX
serial number | Items to be improved | Brief description of the problem | Improvement direction | Improvement person | start date |  | completion date |  | Whether to improve immediately | Confirmor | appendix
[5 empty] | expected | actual | expected | actual
1 | The saturation of the lower glass point Xiaoli Pill is 65% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements。 | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
2 | Bottom glass electrophoresis tank+UVFixed baking operation saturation79.2% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
3 | Xiaoliwan wax+Paste conductive foam+Lower glass glue frame dispensing operation saturation75% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
4 | The upper and lower glass bonding saturation is 67.5% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
5 | Five-in-one front&back saturation53.2% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
6 | CellstickFPCsaturation61.9% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
7 | FPCFoam resistance test saturation40.8% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
8 | The saturation of amplified pills and sports cars is 73.3% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
9 | pointUVglue,UVsolidify&Check saturation33.3% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
10 | Electrophoresis tank noteBufferliquid saturation79.2% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
11 | BufferLiquid injection port sealing and solidification+Water leakage test saturation60.3% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
12 | Silicone oil saturation 50.7% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
13 | Silicone oil port sealing + dispensing + curing saturation 58% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
14 | Set Conn & lower cover + paste QR CODE saturation 41% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
15 | Lock the lid + label the saturation 81.7% | Low job saturation(lower than95%) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
16 | Glass module test saturation 100% | Job saturation 100% | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
17 | Visual inspection of UV glue + pull tape is the bottleneck station | Bottleneck station (the average C/T of the station is the largest) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3.Automated level inspection: simple and automated import 4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-22 | 2024-10-22 | no | LiXX
18 | Measuring oil leakage is the bottleneck station | Bottleneck station (the average C/T of the station is the largest) | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3. Automated level inspection: simple and automated import4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-22 | 2024-10-22 | no | LiXX
20 | The next glass point Xiaoli Pill exists in Renwai Machine 2S | Simultaneous working time of man and machine = manual time (39S) + automatic time (2S) - process standard C/T (41S) = 0S Time of man waiting for machine = automatic time (2S) - simultaneous working time of man and machine (0S) = 2S | 1. Simultaneous operation of man and machine 2.One person, multiple machines working-> Fewer people | openXX | 2024-10-08 | 2024-10-08 | 2024-10-22 | 2024-10-22 | no | LiXX
21 | Dispensing UV glue, UV curing & checking the existence of human machine 22S | Simultaneous working time of man and machine = manual time (20S) + automatic time (22S) - process standard C/T (42S) = 0S Time of man waiting for machine = automatic time (22S) - simultaneous working time of man and machine (0S) = 22S | 1. Simultaneous operation of man and machine 2.One person, multiple machines working-> Fewer people | openXX | 2024-10-08 | 2024-10-08 | 2024-10-22 | 2024-10-22 | no | LiXX
22 | The sum of the saturations of two adjacent processes is less than or equal to 95% | The sum of Sn process saturation and S(n+1) process saturation is less than or equal to 95% | 1. Judgment of value and reduce tasks without added value 2. Inspection of movement quality and human engineering hazards: Reduce the number of movements, work with both hands at the same time, shorten the distance of movements, and make movements easier; eliminate human engineering hazards 3. Automated level inspection: simple and automated import4.Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2024-10-15 | yes | LiXX
19 | Production line balance rate 75.2% | Balance rate is less than 90% | Merge and rearrange new job elements | openXX | 2024-10-08 | 2024-10-08 | 2024-10-22 | 2024-10-22 | no | LiXX
Remark | If after judgment,Improvement projects are projects that can be improved immediately,Attachments reflecting the implementation of improvement measures need to be hung in the attachment column..
Formulas:
actual = [plumXX]
completion date = [plumXX]+7
tabulation = [completion date]