## 1366 CAP Packer Standard Operat
Project
1366 CAP Packer Standard Operation Case | Analysis of projects to be improved
| Project name |  | 1366 CAPPackaging standardization |  |  | admit | Section Chief Xie Tiewen |  | tabulation | Feng Ming
| form type | serial number | Items to be improved (problems) | Analytical methods(A. Process analysis B. Operation analysis C. Action economic principle D. Action analysis E. 5W1H F.5Why or Wn ) | Analysis process (explained in the attachment) | True Cause(KPIVs) |  | Responsible person | start date | completion date | illustrate
| Process capability table | 1 | Look at the appearance | Boperational analysis |  | 1.Left,There is a difference in the working time of the right hand. 2.Doing one-handed work while holding objects,Both hands are held,or the waste of waiting |  | Feng Ming | 12/25.08 | 1/12.09 | 1/12.09Completed
|  | 2 | Plate | Boperational analysis |  |  |  | Feng Ming | 12/25.08 | 1/12.09 | 1/12.09Completed
3
| Standard work combination table | 1 | Look at the appearance | F:Wn |  | 1. Need to check for unsaturated mold defects2. Need to check for bad hair3.Need to check for bad plastic mouth strain |  | Feng Ming | 12/25.08 | 2/5.09 | Completed
2
| standard worksheet | 1
2
Implementation of project countermeasures to be improved
| Project name |  | 1366CAPStandard work |  |  | admit | Guo Zuliang |  |  | tabulation | Feng Ming
| form type | serial number | Items to be improved (problems) | True Cause(KPIVs) |  | Improvement direction(Operation improvement/Equipment improvement) | Propose improvement plans | Plan implementation | Responsible person | start date | completion date | illustrate
| Process capability table | 1 | Look at the appearance | 1.Left,There is a difference in the working time of the right hand 2.Doing one-handed work while holding objects,Both hands are held,or the waste of waiting |  | Work improvement | 1.Perform bimanual work analysis,Reduce grip,waiting time. 2.reduce,Difference in working time between left and right hands. |  | Feng Ming | 1/18.09 | 2/14.09 | Completed
|  | 2 | Plate | [5 empty] | Feng Ming | 1/18.09 | 2/14.09 | Completed
| standard worksheet | 1 | Look at the appearance | 1.Product hair needs to be checked. 2.Need to check if the product is not full. 3.Need to check the lint of the product's glue mouth |  | / | 1.Reduce inspections of bad items. |  | Feng Ming | 12/6.08 | 2/5.09 | Completed
2
| Standard work combination table | 1
2

## 478479 series COVER Packer wor
Project | serial number | Items to be improved | Brief description of the problem | Improvement direction | Improvement person | start date |  | completion date |  | Whether to improve immediately | Confirmor | appendix
1366 CAP Packer Standard Operation Case | [5 empty] | expected | actual | expected | actual
| 1 | Master mold surface inspection | Master mold surface inspection accounts for 10% of the entire operation process68.21% | Simplification of master mold surface inspection work items | Qiu Shuwang | 12/1.08 | 12/1.08 | 12/30.08 |  | no | Section Chief Xie Xiaobing
| 2 | Product wear rod | Product threading accounts for 10% of the entire operation process23.21% | Fixture development replaces manual work | Zhang Hongming | 12/1.08 | 12/1.08 | 12/30.08 |  | no | Section Chief Xie Xiaobing
| NO | Analysis type | Unable to immediately improve the project | wnanalyze | KPIVfilter
| 1 | Process capability table-----value analysis | Master mold surface inspection
Wear rod
side inspection
Hardware inspection
| 2 | standard worksheet----Layout and logistics analysis | There is a problem of taking and putting down during product inspection,Product moves up and down
| 3 | Standard work combination table----saturation analyze | Master mold surface inspection accounts for 68.21% of the entire operation process | Improve through analysis1&2Reduces master mold surface inspection&Ratio of rod threading to total operating time
Product rod threading accounts for 23.21% of the entire operation process
| serial number | Items to be improved | true cause(KPIV)
| 1 | Product master mold surface inspection | Product discoloration
| 2 |  | Product is not full
| 3 | Product hardware inspection | Visual fatigue during inspection
| 4 |  | There is no clear distinction between good and defective products
| 5 | Product manual threading | Assembly requires neatly arranged products
| serial number | Items to be improved | Improvement direction | Improvement plan | feasibility assessment | Evaluation indicators |  |  | Program evaluation | Options
[6 empty] | technology | economy | society
| 1 | Product master mold surface inspection | 1:Reduce the number of checks&frequency | by everypcsChange all inspections to random inspections |  | NG | OK | OK | NG | /
|  |  |  | by everypcsChange all inspections to inspections by time period |  | NG | OK | OK | NG | /
|  |  | 2:Reduce inspection items | Cancel discoloration defect check |  | NG | OK | OK | NG | /
|  |  |  | Cancel unsaturated mold defect check |  | NG | OK | OK | NG | /
|  |  | 3:Optimize inspection method | Check all products before threading the rod |  | NG | OK | OK | NG | /
|  |  |  | After the product is inserted into the pole, the entire product is inspected together. |  | OK | OK | OK | OK | V
| 2 | Product hardware inspection | 1:Reduce the number of checks&frequency/Optimize inspection method | by everypcsChange all inspections to random inspections |  | NG | OK | OK | NG | /
|  |  |  | by everypcsChange all inspections to inspections by time period |  | NG | OK | OK | NG | /
|  |  |  | Combined with the master mold surface inspection and performed at the same time |  | OK | OK | OK | OK | V
| 3 |  | 2:Mold fixture/Hardware piece design change | Hardware shape change |  | OK | NG | NG | NG | /
|  |  |  | Let the variable model be,Realize the anti-fool effect of missing hardware |  | OK | OK | OK | OK | V
| 4 | Product wear rod | 1:Changes in rod threading methods | Check all products before threading the rod |  | NG | OK | OK | NG | /
|  |  |  | Add a jig to replace manual alignment and threading of rods |  | OK | OK | OK | OK | V

## Audio Jack Series
Project | Analysis of projects to be improved
Project to promote standardization of stamping operator operations | Project name |  | Audio JackStandardization of operations for series stamping operators |  |  | admit | Zhong Liwen |  | tabulation | Liu Yufei
| form type | serial number | Items to be improved (problems) | Analytical methods(A. Process analysis B. Operation analysis C. Action economic principle D. Action analysis E. 5W1H F.5Why or Wn ) | Analysis process (explained in the attachment) | True Cause(KPIVs) |  | Responsible person | start date | completion date
| Process capability table | 1 | Appearance inspection during production(Wasted action) | C. Action economy principle |  | Appearance inspection during production involves bending movements, which is a waste of movements. |  | Liu Yufei | 2009-12-12 | 2009-01-16
|  | 2 | Appearance inspection under microscope(Wasted action) | A.process analysis |  | Operator's improper visual inspection method |  | Liu Yufei | 2009-12-12 | 2009-01-16
|  | 3 | Measured dimensions at projector(Long measurement time) | F.Wnanalyze |  | 1.Projector measurements are inaccurate 2.Improper working practices of personnel |  | Zhang Xiaohui | 2009-12-14 | 2009-01-17
| Standard work combination table | 1 | CTtime andTTThe time difference is too large.(Waiting for the machine) | F.Wnanalyze |  | Relatively little operator workload(The cycle time is20min,CTThe time is14.9min) |  | Liu Yufei | 2009-12-15 | 2009-01-12
| standard worksheet | 1 | Appearance and dimensional inspection(Invalid walking) | A.process analysis |  | The position of the microscope is unreasonable, the walking time is long, and there is invalid walking |  | Liu Yufei | 2009-12-22 | 2009-01-15

## Bulk Pin quality
Project | Analysis of projects to be improved
Bulk PIN quality inspection standard case | Project name |  | scatteredPINQuality Assurance InspectionStandardization of work |  |  | admit | Huang Chaoyang |  | tabulation | Chengyuan
| form type | serial number | Items to be improved (problems) | Analytical methods(A. Process analysis B. Operation analysis C. Action economic principle D. Action analysis E. 5W1H F.5Why or Wn ) | Analysis process (explained in the attachment) | True Cause(KPIVs) |  | Responsible person | start date | completion date | illustrate
| Process capability table | 1 | Sample comparison | / | / | / |  |  | 2/23 | 2/24 | Situation Analysis Phase Improved
|  | 2 | CONTDimensions | A.process analysis |  | 1Measuring Equipment Limited ,Concentrated placement; 2.The measurement steps are complicated ; |  | Wang FanChengyuan | 2/23 | 3/12
|  | 3 | data logging | / | / | / |  |  | 2/23 | 2/24 | Situation Analysis Phase Improved
|  | 4 | EChemical operations | / | / | / |  |  | 2/23 | 2/24 | Situation Analysis Phase Improved
| Standard work combination table | 1 | Too many people moving around | / | / | Same process capability table |  |  | 2/23 | 3/12
|  | 2 | Invalid waiting time is long | / | / | Same process capability table |  |  | 2/23 | 3/12
| standard worksheet | 1 | CONTDimensions | / | / | Same process capability table |  |  | 2/24 | 3/12
|  | 2 | EChemical operations | / | / | / |  |  | 2/23 | 2/24 | Situation Analysis Phase Improved
Implementation of project countermeasures to be improved
| Project name |  | scatteredPINQuality Assurance InspectionStandardization of work |  |  | admit | Huang Chaoyang |  |  | tabulation | Chengyuan
| form type | serial number | Items to be improved (problems) | True Cause(KPIVs) |  | Improvement direction(Operation improvement/Equipment improvement) | Propose improvement plans | Plan implementation | Responsible person | start date | completion date | illustrate
| Process capability table | 1
|  | 2 | ContDimensions | 1Measuring Equipment Limited ,Concentrated placement; 2.The measurement steps are complicated ; |  | Equipment improvements |  |  | Wang Fan/Chengyuan | 2/23 | 3/12 | Working time can be determined by137secdown to31sec,Down81.4%.
3
4
| Standard work combination table | 1
2
| standard worksheet | 1
2

## Dome machine
Project | Project name |  | domeStandardization of machine operation operations |  |  | admit | Assistant Manager Lin Wenquan |  | tabulation | Liu Jianling
Dome machine operator work standardization plan | form type | serial number | Items to be improved (problems) | Analytical methods(A. Process analysis B. Operation analysis C. Action economic principle D. Action analysis E. 5W1H F.5Why or Wn ) | Analysis process (explained in the attachment) | True Cause(KPIVs) |  | Responsible person | start date | completion date | illustrate
| Process capability table | 1 | DomeFunctional testing(Wasted action) | A.process analysis |  | every timeDomeFunctional measurement data needs to be copied,andDOMEImproper use of fixtures |  | Shi Qingjie | 2009-02-02 | 2009-02-12 | The estimated functional measurement time after improvement is4.9minreduced to4.27min
| Standard work combination table | 1 | CT time andTTThere is a difference in time(There are people waiting for the machine to waste) | F.Wn |  | Relatively little operator workload(The cycle time is36min,CTThe time is26.1min) |  | Shi Qingjie | 2009-02-02 | 2009-02-12
| standard worksheet | 1 | Product function self-inspection personnel move around and wait a lot(There is a waste of waiting) | / | / | Product function self-test,There is a problem of wastage of personnel |  | Shi Qingjie | 2009-01-05 | 2009-01-15 | 1.In the current situation analysis stageAppearance inspectionand preliminaryDOMEFunctional inspection completed and improved; 2.Completed during the problem analysis phaseDOMEFunctional testfurther improvements;
2
Implementation of project countermeasures to be improved
| Project name |  | domeStandardization of machine operation operations |  |  | admit | Assistant Manager Lin Wenquan |  |  | tabulation | Liu Jianling
| form type | serial number | Items to be improved (problems) | True Cause(KPIVs) |  | Improvement direction(Operation improvement/Equipment improvement) | Propose improvement plans | Plan implementation | Responsible person | start date | completion date | illustrate
| Process capability table | 1 | DomeAppearance and functional inspection(Repeated waste) | High number of self-checks,Causes duplication of time and waste; |  | Work improvement | Reduce the number of appearance and functional tests of self-inspection | Every10Kconduct3The appearance and function inspections are reduced to 2 appearance and function inspections every 10K; | Shi Qingjie | 2009-02-02 | 2009-02-12 | After this stage of improvement, each operation time is divided into the time spent in the appearance and function inspection of the analysis stage.22.8 minutesReduced to the countermeasure implementation stage17.3min,Down24.1%
| Standard work combination table | 1 | CTtime andTTThere is a difference in time(There are people waiting for the machine to waste) | Operators have relatively less workload; |  | Work improvement | Increase operator workload,Increase job saturation |  | Shi Qingjie | 2009-02-02 | 2009-02-12 | By rearranging operator work,The operator's saturation is given by69.4%promoted to90.5%
2
| standard worksheet | 1
2